## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | ModuleNotFoundError: No module named 'workflows' occurred while running the Streamlit application. | Sprint 1 | Bhupesh Kumar | Configuration / Path | Changed to the correct project directory before running Streamlit and verified the workflows package location. | 2026-09-05 | Closed | Application started successfully
|  |  | ModuleNotFoundError: No module named 'dotenv' occurred when loading environment variables. | Sprint 1 | Bhupesh Kumar | Dependency | Installed python-dotenv in the virtual environment and verified the import. | 2026-09-05 | Closed | Environment variables loaded successfully
|  |  | ModuleNotFoundError: No module named 'langchain_google_genai' occurred while connecting Gemini with LangChain. | Sprint 1 | Bhupesh Kumar | Dependency | Installed the langchain-google-genai package and verified the Gemini integration. | 2026-09-05 | Closed | Gemini package working
|  |  | Gemini returned API_KEY_INVALID while testing the LLM connection. | Sprint 1 | Bhupesh Kumar | Configuration / API | Configured the Gemini API key correctly in the .env file and verified the API key loading. | 2026-09-06 | Closed | API authentication resolved
|  |  | Gemini model availability error occurred because the configured model was not available for the account. | Sprint 1 | Bhupesh Kumar | API / Configuration | Updated the configured Gemini model to the available model and tested the LLM connection again. | 2026-09-06 | Closed | LLM response generated successfully
|  |  | Gemini response was displayed with raw structured content and signature metadata in the Streamlit UI. | Sprint 1 | Bhupesh Kumar | UI / Response Handling | Added response text extraction and displayed only the readable AI-generated content using Streamlit Markdown. | 2026-09-06 | Closed | Clean Business Analysis and Recommendation displayed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others